[Startup / Project Name]

[One-line description  |  Sector  |  Stage  —  e.g. Edge-AI diagnostic device for point-of-care stroke detection  |  MedTech / AI  |  Seed → Series A]

Monthly Update — [Month, Year]  |  Submitted by [Name, Role]  |  ARTPARK POC: [Name]  |  Confidential

# 1. Executive Summary

5 bullets. If your ARTPARK POC only reads this section, they should know whether you're on track. Write this last.

- Headline win: e.g. Received CDSCO manufacturing licence; first hospital deployment at AIIMS Delhi went live with 12 patients scanned in week 1.

- Biggest concern: e.g. ASIC v0.2 tape-out yield came in at 61% vs 75% target — silicon cost/unit is $28 vs $22 planned. Mitigation in §5.

- Commercial: e.g. ₹22L device sales + ₹8L annual service this month; 2 new hospital contracts signed at Fortis and Manipal.

- Cash: e.g. ₹18.3 Cr in bank, 11 months runway; Series A term sheet expected in 3 weeks.

- Top ask from ARTPARK this month: e.g. 3 named hospital-chain intros + a CDSCO regulatory advisor. Details in §8.

# 2. Key Metrics

Fill in your numbers. Keep the metric list stable month-on-month — do not change definitions to make things look better. Add rows for your business-specific KPIs.

Colour coding for Commentary column: green = ahead / on plan  ·  amber = behind but recoverable  ·  red = blocked / material risk

| Metric | Target | Actual | vs Last Mo | Commentary |
| --- | --- | --- | --- | --- |
| Commercial |  |  |  |  |
| Revenue this month (₹ Lakh) | [ ] | [ ] | [ ] | [one-line commentary] |
| Active paying customers / pilots | [ ] | [ ] | [ ] | [one-line commentary] |
| New LOIs / MoUs signed | [ ] | [ ] | [ ] | [one-line commentary] |
| Weighted pipeline (₹ Lakh) | [ ] | [ ] | [ ] | [one-line commentary] |
| Product / Technology |  |  |  |  |
| Deployments in field | [ ] | [ ] | [ ] | [one-line commentary] |
| Key product metric #1 | e.g. accuracy, uptime | [ ] | [ ] | [one-line commentary] |
| Key product metric #2 | e.g. BOM cost, latency | [ ] | [ ] | [one-line commentary] |
| TRL Level (1–9) | [ ] | [ ] | [ ] | [one-line commentary] |
| Financials |  |  |  |  |
| Cash in bank (₹ Cr) | [ ] | [ ] | [ ] | [one-line commentary] |
| Net burn / month (₹ Lakh) | [ ] | [ ] | [ ] | [one-line commentary] |
| Runway (months) | [ ] | [ ] | [ ] | [one-line commentary] |
| Team |  |  |  |  |
| Headcount (end of month) | [ ] | [ ] | [ ] | [one-line commentary] |
| Net hires this month | [ ] | [ ] | [ ] | [one-line commentary] |

# 3. Technical, Product & Regulatory Milestones

The most important section for a deeptech at Seed / early-Series-A stage — technical progress is a stronger signal of health than revenue. Include what shipped this month (mark "Done") as well as active and upcoming milestones. Carry the same list forward month-to-month so trajectory is visible.

| Milestone | Owner | Status | Notes |
| --- | --- | --- | --- |
| [milestone description] | [owner] | [Done/On Track/At Risk/Blocked] | [brief note] |
| [milestone description] | [owner] | [Done/On Track/At Risk/Blocked] | [brief note] |
| [milestone description] | [owner] | [Done/On Track/At Risk/Blocked] | [brief note] |
| [milestone description] | [owner] | [Done/On Track/At Risk/Blocked] | [brief note] |
| [milestone description] | [owner] | [Done/On Track/At Risk/Blocked] | [brief note] |
| [milestone description] | [owner] | [Done/On Track/At Risk/Blocked] | [brief note] |

# 4. Commercial & Customer Traction

## 4.1 Pilots and customers

Write in short prose or bullets. Cover where things sit in the LOI → paid pilot → commercial contract funnel, and any conversions or losses this month.

- Active paid pilots: e.g. ITC Agri (2 districts in MP); Godrej Agrovet (Nashik); UPL (Punjab); Mahindra Agri (Karnataka).

- Conversions this month: e.g. ITC pilot → 3-year MSA signed, ₹4.2 Cr TCV, 40 drones + spraying-as-a-service. Or "none this month".

- Pipeline: e.g. 9 qualified state-agri-dept opportunities; 3 in advanced discussion. Weighted pipeline ₹12 Cr over 6 months.

- Losses: e.g. Lost Rallis pilot to competitor on payload spec (10L vs our 8L); payload v2 in build. Or "none".

## 4.2 What the market taught us this month

Two short bullets. This is where you show ARTPARK you're learning, not just executing.

- Sharpest wedge: e.g. Cash-crop belts with ≥50-acre farms and existing FPO structures — decision cycles under 60 days.

- What isn't working: e.g. Direct-to-farmer sales; every deal that closes runs through an FPO or agri-input distributor.

# 5. Lowlights & Risks

The credibility section. Cover 2–4 real issues, honestly, with mitigation plans. Hiding lowlights makes the good news less believable. Format each as: what happened → impact → what we're doing about it.

- Risk 1 (red / blocked): e.g. ASIC yield at 61% vs 75% target on v0.2 tape-out. Impact: cost/unit at $28 vs $22 planned, pushes SDK-3 launch by one quarter. Mitigation: DFT rework + yield-improvement pass with TSMC; v0.3 tape-out shifted to Q3.

- Risk 2 (amber / at risk): e.g. CDSCO manufacturing licence audit — one non-critical observation on batch documentation. Impact: possible 3-week delay on commercial launch. Mitigation: CAPA filed, revalidation scheduled for 18-Feb.

- Risk 3 (amber): e.g. Single-source ToF sensor supplier flagged 12-week lead time (global demand surge). Impact: constrains ramp beyond 40 units/month. Mitigation: qualifying second-source; 3-month buffer stock built.

# 6. Team & Hiring

Short prose. Named hires and specific open roles are more useful than headcount alone.

- Headcount: e.g. 22 (+3 this month).

- Joined this month: e.g. VP Regulatory (ex-Wipro GE Healthcare); Senior RTL Engineer (ex-Intel Bangalore); Field Applications Engineer. Or "none".

- Left this month: e.g. 0 regretted; 1 non-regretted (early hire, mutual). Or "none".

- Open roles (urgent first): e.g. Head of Clinical Affairs (ex-Philips/Siemens Healthineers); Analog Design Lead; Regulatory Affairs Manager; 2× Firmware Engineers.

# 7. Financials & Fundraising

## 8.1 This month's snapshot

- Revenue: e.g. ₹22L device sales + ₹8L annual service + ₹4L NRE from a strategic partner = ₹34L total.

- Gross margin: e.g. 41% on devices (target 55% at scale); services at 68%. Blended 44%.

- Cash burn: e.g. ₹95L net this month vs ₹110L plan (underspend on delayed silicon tape-out). YTD burn ₹11.2 Cr.

- Cash balance & runway: e.g. ₹18.3 Cr in bank; 11 months at current burn (9 months at planned burn).

## 8.2 Fundraising status

- Round in progress: e.g. Series A, ₹65–85 Cr target; term sheet with tier-1 fund expected in 3 weeks.

- Investor conversations: e.g. 8 active conversations; 2 term sheets in; expected close in 8–10 weeks.

- Non-dilutive capital: e.g. BIRAC BIG grant (₹50L) sanctioned; DST-NIDHI PRAYAS Phase-2 in review; MeitY chip-design incentive application drafted. Or "none this month".

# 8. Asks from ARTPARK

List your top 2–4 asks for the month, in priority order. Be specific and named — "customer intros" is hard to action; "intro to VP Ops at Company X" gets results. Don't list one ask per category unless you genuinely need help in each — a focused shortlist works better than an exhaustive one.

Prompt (pick the categories that apply): customer / partnership intros  ·  investor intros  ·  hiring referrals  ·  ARTGarage / facility  ·  IISc labs / faculty  ·  non-dilutive capital  ·  regulatory / policy  ·  advisor time.

- 1. e.g. Intro to Head of Digital Transformation at Fortis Healthcare — we're in early conversations, warm intro would accelerate. Happy to send a 1-pager.

- 2. e.g. Head of Clinical Affairs hire — ex-Philips / Siemens Healthineers or similar. Referrals from your network hugely welcome.

- 3. e.g. 30 min with someone who has taken a Class II medical device through CDSCO and FDA 510(k) — we're at the CDSCO audit stage and would value a sanity check.

- 4. e.g. EMI/EMC chamber slot at ARTGarage in Feb-W3 for pre-compliance testing.  (Add more numbered asks if needed.)

# 9. Happy News & Demos

Optional but encouraged. A great customer story, an award, a demo worth showing off. Links to short videos or dashboards where possible.

- Field story: e.g. Our device detected an early-stage stroke at a Tier-2 hospital in Vizag; patient received tPA within the golden hour. Radiologist sent a note. Or leave blank.

- Recognition: e.g. Featured in YourStory's "Deeptech to Watch 2026"; won Best AI Innovation at MedTech Conclave; NITI Aayog citation on chip-design self-reliance. Or "none this month".

- Demos & links: [Video: <device in ER at partner hospital>]  ·  [Photo: <silicon wafer / test board / drone in field>]  ·  [Dashboard: <live deployment metrics>]

[Company Legal Name]  ·  Confidential — for ARTPARK portfolio use only.  ·  Submitted by [Name, Role, email]